LDO Report 22nd August 2006

HOUSING

Housing Survey – A housing survey has been completed by HSCHT for each community council area.

Information Days - Housing Information Days were held in Dunbeath on 13th June 06 where 17 people attended and Lybster on 21st June where 24 people attended.

Land Audit – A land audit has been completed by HSCHT for both community council areas.  (Both Community Councils provided information on potential sites for housing.)

Housing Needs - Meetings have been held between HSCHT, Pentland Housing Association and Highland Council to discuss a way forward.  (Ongoing)

Housing Audit – A report is currently being carried out by HSCHT, photo, age and condition of house is being recorded.

Dunbeath Tennis Court

Funding has been provided by CASE, Awards for All, Dunbeath Community Council and Dunbeath Community Centre.

All work on the Tennis court has now been completed.  Fun raising in the local shop provided a new net.  The official opening ceremony took place on Monday 14th August 06.

Dunbeath Football Pitch Fence – The fence between football pitch and Portormin Road has been completed.  Funding has been provided by CASE.

Lybster Playgroup Premises / Drop In Centre for the Youth – The proposed hall extension is on hold.

The committee would like an ISO container that would be used to store hall equipment.  The ISO container would be located at the rear of the hall.

LDO has information on ISO containers – to meet with Community Centre chairman to discuss further.

Day Care Centre Dunbeath –.

A 1 year pilot scheme has been agreed with Caithness Rural Transport for provision of a 5 seater vehicle with wheelchair access.

The vehicle was delivered on 10th May 06 and all concerned are happy with the vehicle.

The vehicle has been MOT’d and minor repairs carried out.

Youth

Lybster - Funding for a youth leader at Lybster has been agreed with HC for 5 hours per week for 40 weeks.  This post is to be advertised in the near future.

Corresponding with HC re advertising youth leader post, start date etc.

A meeting is to be arranged to see if there is interest in forming a youth club within Dunbeath.  A committee and youth leaders need to be identified.

Footpaths –

Lybster - Brethren Well - Andrew Gunn/Lybster Community Council have completed this project.

Dunbeath - Strath Pathway phase 1 – awaiting information form George Bethune.

Transport – It was agreed a working group be formed to progress this project:  Gladys Lyon, Eann Sinclair (CASE), Alison Gunn and LDO.

The day care centre vehicle continues to operate successfully.

The additional services for Rapsons buses are being used, especially by the youth.

Renewable Energy

Working Group

Iain Gunn, Andrew Gunn, Niall Smith, Neil Buchanan, James Georgeson, Carole Darmady, Eric Larnach.

After meetings with Elizabeth Marshall - Heat and Power scheme in Wick, site visits to Borgie Forest, Forsinard Forest and Abriachan Forest, several meeting with Forestry Commission and an Options Appraisal Report it was agreed the group should progress with the option of a community owned small wind power scheme.

A meeting was held in Dornoch FC office with Chris Nixon, Donald Maclellan and Tim Cockeril new area manager.  Topics discussed were the proposed sites for a small wind power scheme, cost of the land, a management agreement and public consultation process.

Sandra Holmes indicated the existing land fund is finishing and that a fund “Investing in Communities” is to be launched shortly, once she has the details she will contact LDO to arrange a meeting.

Jon Priddy CEC has provided a map with possible grid connections.

Stephen Fraser conducted the drive and talk visit to Rumster Outdoor Centre.  The visit included a site identified by the development group as a possible location for a small community wind scheme.

FC have been supplied with SECDG Constitution, marked up copy of a map indicating area of forest for a small wind power scheme, letter of support from Lybster Community Council, and letter from SECDG.

Forestry Commission District Manager Tim Cockerill has confirmed he has sent a letter of support to Forestry Commission Estates Department to price 40 hectares of land in the North West area of Golticlay Forest.  Donald McLellan FC area land agent has contacted the District Valuer to price the land.  (On hold).

Latheron, Lybster and Clyth Community Development Company

To progress projects in the Latheron, Lybster and Clyth Community Council Area it was agreed to set up a Company Limited by Guarantee. The name of the company is Latheron, Lybster and Clyth Community Development Company.  Legibility for membership of the company is post code areas KW3 and KW5.  Memorandum and Articles written and approved.

Application to Companies House approved.

Application for start up grant from Sandra Holmes Community Land Unit has been approved.

Bank account has been opened.

Halls

Jon Priddy conducted site visits to the local halls regarding renewable energy options.

He has provided basic information on possible options available.

Hall committees have been provided with the information.

Rumster Outdoor Centre

Wednesday 8th March - LDO gave presentation on SECDG projects to Rumster Outdoor Centre Management Group.

No update available – Paul Worthington.

Dunbeath Community Council – Playing Fields

LDO is sourcing funding to provide additional equipment for 1 to 5 year olds through provision of 2 Springers and a Seesaw.  Highland Council have agreed to install and maintain any new equipment in the playing field.

Food for Thought

Interest has been shown in the Lybster area for polytunnels, and a quote has been provided.

A quote has been provided for surrounding fence.

There is interest in Latheron area for a project - Douglas is sourcing suitable bags and compost.  He is also gathering information on potential crops.

Anyone who would like further information should contact Douglas at:

Douglas Henderson, Food for Thought, Telford House, Williamson Street, Wick, KW15ES Work tel: 01955609965 Email: douglas@cvg.org.uk

Mobile Sheep Dipper & Mobile Cattle Crush – meeting to be arranged with Magnus Henderson and existing buying group.

Magnus Henderson has indicated he will require assistance after the lambing in 2006, to further this project.

Lybster Outdoor Bowling Club

Application for funding has been approved by Awards for All.

Committee to contact contractor on preferred option after installation of 2 different types of heater for a trial period.

Jon Priddy provided information on renewable energy after recent site visit.

Lybster Golf Club

New equipment has been identified by the Golf Club as essential since the introduction of the Primary School coaching project.  LDO is sourcing funding for the new equipment.  CASE has agreed to support this project.

Application to Awards for All was unsuccessful.  Another application is being prepared.

Meeting held with John Gunn re purchase of the Golf Course and adjacent land, and to improve/extend the Golf Course.

Lybster Junior Football Club

Barclays sports application has been completed.

Application for kit and sports equipment has been approved.  Items have been selected (awaiting delivery), promotional issues being addressed.

Dunbeath Community Council

Supplied information on grass cutting equipment and sheds.

Suitable equipment identified.

Suitable storage shed identified.

Site visit to possible location of shed.  Estimate required for preparing site.

Funding application being prepared for Awards for All programme.

Lybster Senior Football Club – Refurbishment of Football Pitch

Representatives from the Football Club have indicated on interest in the refurbishment of the football pitch and surrounding areas.  LDO has supplied information on shelters/dugouts, goal posts and nets.  A major problem is no retaining fence to prevent the football disappearing into very, very long grass where on occasion several players attempt to find the ball.  Further meeting to be arrange.

Local Development Plan

It was agreed to progress projects wherever possible.  We may need to prioritise projects at a later date.

Eric Larnach

Local Development Officer

Old School House

Dunbeath

KW6 6ED

Tel: 01593731455

Email:  ericlarnachiate@btconnect.com